## Sheet1
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | Week 1 started on the 6th of Febuary (Sat)
Work was done on the Project Report (Section A + B)
The solution to the problem was defined and planning for the software was done
Research was done on how to design an effective User Interface | [11 empty] | Start dates for each week: | Week 1 | 2021-06-02
Testing compatibility of project files between school and home (due to different versions of VS) | [12 empty] | Week 2 | 13/2
Different sketches were made on how to design the application's UI and features | [12 empty] | Week 3 | 20/2
Various menus for the program, including Main Menu and Settings, were designed | [12 empty] | Week 4 | 27/2
Planning was done on how to implement a system to take a list of words from a text file, then randomise it | [12 empty] | Week 5 | 2021-06-03
The word randomiser module was implemented into the program | [12 empty] | Week 6 | 13/3
Progress was made on the Word Memory game and the various menus associated with it | [12 empty] | Week 7 | 20/3
Planning was done on how to implement an image matching system for the Image Match game | [12 empty] | Week 8 | 27/3
A break was taken over these two weeks in order to focus on the upcoming assessment week | [12 empty] | Week 9 | 2021-03-04
Progress restarted on the Image Match game and the modules associated with it | [12 empty] | Week 10 | 2021-10-04
Work was also done in allowing the user to play customised versions of the two included games | [12 empty] | Week 11 | 17/4
A way to customise the Boggle application itself was added with 3 different "themes"
All of the backgrounds for menus were redrawn and redone for a nicer looking UI
The solution was thoroughly tested in order to fix bugs and issues before the final build
Audio was added to the program with the use of menu sound effects and background music.
All aspects of the software assignment were finalised, and submitted for marking